## Service Steps
Step Order | Step Name(optional) | Task Order | Task Name | Default Duration Days(optional) | Reference Doc Name(optional) | Reference Doc Link(optional)
1 |  | 1 | Conduct training on time and motion study of all stake holders, all union representatives, supervisors and workers if demanded by client. |  | Training Materials | https://docs.google.com/presentation/d/1XZon2O8WIA9k4kyzaL9U1eCvUdGXjcZz/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
2 |  | 1 | Select the work to be studied
|  | 2 | Record all the information about the job |  | Information sheet | https://docs.google.com/spreadsheets/d/1FZF5tcYE-dTIZuAPdgf4mMrMIVJ06VvQ/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
|  | 3 | 1. Record information related to 3M's (Man, Machine and Material) |  | Information sheet | https://docs.google.com/spreadsheets/d/1FZF5tcYE-dTIZuAPdgf4mMrMIVJ06VvQ/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
|  | 4 | 2. Also note the working condition, temperature, humidity, sound etc |  | Information sheet | https://docs.google.com/spreadsheets/d/1FZF5tcYE-dTIZuAPdgf4mMrMIVJ06VvQ/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
3 |  | 1 | Breakdown the operation into elements
|  | 2 | 1. For each job, a detailed breakdown of activities proves helpful
4 |  | 1 | Measure the time by means of a stop watch taken by the operator to perform each element of operation. ​
|  | 2 | 1. Note the observed time
|  | 3 | 2. Compute the rating factor
|  | 4 | 3. Refer the rate of working on the principal rate scale |  | Principal rate scale | https://drive.google.com/file/d/1ncb9Dyu5_qQ8vajtzgBHIoSqqjlVIx3g/view?usp=drive_link
|  | 5 | 4. Refer the number of cycles to be studied (wref ILO guidelines) |  | No. of cycles | https://drive.google.com/file/d/1hkrphMaF83ybPWE1lMbkTn9nO7wRFrAk/view?usp=drive_link
|  | 6 | 5. Capture real time photos and videos if necessary
|  | 7 | 6. Input the necessary data to the time study sheet |  | Time study sheet | https://docs.google.com/spreadsheets/d/1-MPIIT4k6aBTcQmiJx7CK7fvsJLhkJR2/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
5 |  | 1 | Adjust the observed time by rating factor to obtain basic time for each element
|  | 2 | 1. Remove all abnormal readings from the study. Abnormal reading are those which are exceptionally high or low compare to rest of the elemental readings
|  | 3 | 2. Calculate average elemental time
|  | 4 | 3. Multiply average time by rating factor to get basic time for each element
|  | 5 | 4. standard rating is usually kept as 100
|  | 6 | 5. Classify the activities based on VA, RNVA and NVA
|  | 7 | 6. elemental rating could be cycle wise or one effective rating for entire element
6 |  | 1 | Add frequencies of each element (if present)
7 |  | 1 | Add necessary allowances
|  | 2 | 1. Consider each and every allowance type and calculate the point allowance accordingly |  | Allowance datasheet | https://docs.google.com/spreadsheets/d/1EdyVSUwXAkhh_A3m7518vDR0LNfWIVgb/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
|  | 3 | 2. Convert the point allowance to percent allowance |  | Point to percent conversion table | https://drive.google.com/file/d/1RWgmlQ1-dDeQYK1G834bJjgsdRZx8JRU/view?usp=drive_link
8 |  | 1 | Compute the standard time
|  | 2 | 1. Multiply effective basic time with allowance percent obtained
9 |  | 1 | Review the activities based on VA, RNVA and NVA
10 |  | 1 | Make a list of all identified kaizens in the process or layout studied |  | Kaizen template with ROI | https://docs.google.com/spreadsheets/d/1BxghQI_SllmPGaxmdmgaQg8v1nGwXlK5/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
|  | 2 | 1. Manpower optimization through Line balancing/No cost kaizen |  | Kaizen template with ROI | https://docs.google.com/spreadsheets/d/1BxghQI_SllmPGaxmdmgaQg8v1nGwXlK5/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
|  | 3 | 2. Manpower optimization through Low-cost Kaizen |  | Kaizen template with ROI | https://docs.google.com/spreadsheets/d/1BxghQI_SllmPGaxmdmgaQg8v1nGwXlK5/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
|  | 4 | 3. High-cost Kaizen |  | Kaizen template with ROI | https://docs.google.com/spreadsheets/d/1BxghQI_SllmPGaxmdmgaQg8v1nGwXlK5/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
11 |  | 1 | Implement the ROI analysis on low cost and high cost kaizen respectively. |  | Kaizen template with ROI | https://docs.google.com/spreadsheets/d/1BxghQI_SllmPGaxmdmgaQg8v1nGwXlK5/edit?usp=drive_link&ouid=115536764670123174230&rtpof=true&sd=true
12 |  | 1 | Prepare a time study summary sheet